## 📡 API Tracker
🚢 GR-Class Maritime Certification System — Complete API Progress Tracker
Last Updated: 15 Apr 2026 ¦ Total APIs: 220 ¦ Modules: 35
# | Method | API Endpoint | Description | Role Access | 🖥 Backend | 🖱 Frontend | Notes / Blockers
🔐 Authentication [/api/v1/auth]
1 | POST | /api/v1/auth/login | User login (returns access + refresh token) | Public | Done | Done
2 | POST | /api/v1/auth/logout | Logout (invalidate session) | All | Done | Done
3 | POST | /api/v1/auth/refresh-token | Get new access token via refresh token | All | Done | Pending
4 | POST | /api/v1/auth/forgot-password | Send password reset email/OTP | Public | Done | Done
5 | POST | /api/v1/auth/reset-password | Reset password with token | Public | Done | Done
6 | POST | /api/v1/auth/change-password | Change current password (logged in) | All | Done | Pending
👤 Users [/api/v1/users]
7 | GET | /api/v1/users/me | Get own profile | All | Done | Done
8 | PUT | /api/v1/users/profile-pic | Update profile picture (multipart) | All | Done | Pending
9 | PUT | /api/v1/users/fcm-token | Update Firebase push notification token | All | Done | Pending
10 | GET | /api/v1/users | List all system users | ADMIN | Done | Pending
11 | POST | /api/v1/users | Create new internal user | ADMIN | Done | Pending
12 | PUT | /api/v1/users/:id | Update user details | ADMIN | Done | Pending
13 | PUT | /api/v1/users/:id/status | Enable or disable user account | ADMIN | Done | Pending
14 | DELETE | /api/v1/users/:id | Delete user permanently | ADMIN | Done | Pending
🏢 Clients [/api/v1/clients]
15 | GET | /api/v1/clients/profile | Client: get own profile | CLIENT | Done | Pending
16 | PUT | /api/v1/clients/profile | Client: update own profile | CLIENT | Done | Pending
17 | GET | /api/v1/clients/profile/documents | Client: get own uploaded documents | CLIENT | Done | Pending
18 | GET | /api/v1/clients/dashboard | Client: own dashboard & stats | CLIENT | Done | Pending
19 | POST | /api/v1/clients | Create new client account | ADMIN,GM,TM | Done | Pending
20 | GET | /api/v1/clients | List all clients | ADMIN,GM,TM,TO | Done | Pending
21 | GET | /api/v1/clients/:id | Get client by ID | ADMIN,GM,TM,TO | Done | Pending
22 | GET | /api/v1/clients/:id/documents | Get documents uploaded by client | ADMIN,GM,TM,TO | Done | Pending
23 | PUT | /api/v1/clients/:id | Update client info | ADMIN,GM,TM | Done | Pending
24 | DELETE | /api/v1/clients/:id | Delete client | ADMIN | Done | Pending
🚢 Vessels [/api/v1/vessels]
25 | GET | /api/v1/vessels | List all registered vessels | ADMIN,GM,TM,TO,CLIENT | Done | In Progress
26 | GET | /api/v1/vessels/client/:clientId | Get vessels belonging to specific client | ADMIN,GM,TM | Done | Pending
27 | POST | /api/v1/vessels | Create / register new vessel | ADMIN,GM,TM | Done | In Progress
28 | GET | /api/v1/vessels/:id | Get vessel details by ID | ADMIN,GM,TM,TO,SURV,CLIENT | Done | Pending
29 | PUT | /api/v1/vessels/:id | Update vessel information | ADMIN,GM,TM | Done | Pending
🔍 Surveyors [/api/v1/surveyors]
30 | GET | /api/v1/surveyors/get-upload-url | Get S3 presigned URL for application docs | Public | Done | Pending
31 | POST | /api/v1/surveyors/apply | Submit surveyor application (public) | Public | Done | Pending
32 | GET | /api/v1/surveyors | List all approved surveyors | ADMIN,GM,TM | Done | Pending
33 | POST | /api/v1/surveyors | Directly create surveyor account | ADMIN,TM | Done | Pending
34 | GET | /api/v1/surveyors/applications | List pending surveyor applications | ADMIN,TM | Done | Pending
35 | PUT | /api/v1/surveyors/applications/:id/review | Approve or reject application | TM,ADMIN | Done | Pending
36 | PUT | /api/v1/surveyors/:id/status | Activate or deactivate surveyor | ADMIN,TM | Done | Pending
37 | GET | /api/v1/surveyors/:id/profile | Get full surveyor profile | ADMIN,TM,SURV,GM | Done | Pending
38 | PUT | /api/v1/surveyors/:id/profile | Update surveyor profile | ADMIN,TM | Done | Pending
39 | POST | /api/v1/surveyors/availability | Surveyor marks own availability | SURVEYOR | Done | Pending
40 | POST | /api/v1/surveyors/location | Report live GPS location | SURVEYOR | Done | Pending
41 | GET | /api/v1/surveyors/:id/location-history | View GPS history of surveyor | ADMIN,TM,GM | Done | Pending
💼 Jobs [/api/v1/jobs]
42 | GET | /api/v1/jobs | List jobs (filtered by role) | All | Done | In Progress
43 | POST | /api/v1/jobs | Create new job/survey request | CLIENT,ADMIN,GM | Done | In Progress
44 | GET | /api/v1/jobs/:id | Get job full details | All | Done | Pending
45 | PUT | /api/v1/jobs/:id/verify-documents | TO verifies submitted client documents | ADMIN,TO,GM | Done | Pending
46 | PUT | /api/v1/jobs/:id/approve-request | GM/ADMIN approves job request | ADMIN,GM | Done | Pending
47 | PUT | /api/v1/jobs/:id/finalize | TM finalizes job after survey | ADMIN,GM,TM | Done | Pending
48 | PUT | /api/v1/jobs/:id/assign | GM assigns surveyor to job | ADMIN,GM | Done | Pending
49 | PUT | /api/v1/jobs/:id/reassign | GM reassigns surveyor | ADMIN,GM | Done | Pending
50 | PUT | /api/v1/jobs/:id/reschedule | GM reschedules job date/time | ADMIN,GM | Done | Pending
51 | PUT | /api/v1/jobs/:id/authorize-survey | Authorize surveyor to begin work on-site | ADMIN,GM,TM | Done | Pending
52 | PUT | /api/v1/jobs/:id/review | TO reviews completed survey | ADMIN,TO | Done | Pending
53 | PUT | /api/v1/jobs/:id/send-back | Send job back for corrections | ADMIN,TM,TO | Done | Pending
54 | PUT | /api/v1/jobs/:id/reject | Reject job request | ADMIN,GM,TM | Done | Pending
55 | PUT | /api/v1/jobs/:id/cancel | Cancel job | CLIENT,GM,TM,ADMIN | Done | Pending
56 | PUT | /api/v1/jobs/:id/priority | Update job priority level | ADMIN,GM,TM | Done | Pending
57 | GET | /api/v1/jobs/:id/history | Full lifecycle / audit history of job | ADMIN,GM,TM,TO | Done | Pending
58 | POST | /api/v1/jobs/:id/notes | Add internal note (not visible to client) | ADMIN,GM,TM,TO | Done | Pending
59 | GET | /api/v1/jobs/:id/messages/external | List external (client-visible) messages | All | Done | Pending
60 | GET | /api/v1/jobs/:id/messages/internal | List internal team messages | ADMIN,GM,TM,TO | Done | Pending
61 | POST | /api/v1/jobs/:id/messages | Send job message (with optional attachment) | All | Done | Pending
📋 Surveys [/api/v1/surveys]
62 | POST | /api/v1/surveys | Surveyor creates survey record for job | SURVEYOR | Done | Pending
63 | POST | /api/v1/surveys/submit | Surveyor submits final survey | SURVEYOR | Done | Pending
64 | GET | /api/v1/surveys | List surveys (with filters) | ADMIN,GM,TM,TO | Done | Pending
65 | PUT | /api/v1/surveys/:id | Update survey data (draft) | SURVEYOR | Done | Pending
66 | POST | /api/v1/surveys/:id/findings | Add finding/observation to survey | SURVEYOR | Done | Pending
67 | PUT | /api/v1/surveys/:id/review | TO/TM reviews and approves survey | TO,TM,ADMIN | Done | Pending
68 | GET | /api/v1/surveys/:id | Get survey by ID | ADMIN,GM,TM,TO,SURV | Done | Pending
✅ Checklists [/api/v1/checklists]
69 | GET | /api/v1/checklists/jobs/:jobId | Get checklist assigned to a job | All | Done | Pending
70 | PUT | /api/v1/checklists/jobs/:jobId | Surveyor submits completed checklist | SURVEYOR | Done | Pending
📝 Checklist Templates [/api/v1/checklists/templates]
71 | POST | /api/v1/checklists/templates | Create new checklist template | ADMIN,TM | Done | Pending
72 | GET | /api/v1/checklists/templates | List all checklist templates | ADMIN,GM,TM | Done | Pending
73 | GET | /api/v1/checklists/templates/:id | Get template details | ADMIN,GM,TM,SURV | Done | Pending
74 | GET | /api/v1/checklists/templates/master-file/:id | Download/view master template file URL | ADMIN,TM | Done | Pending
75 | PUT | /api/v1/checklists/templates/:id | Update template content/metadata | ADMIN,TM | Done | Pending
76 | PUT | /api/v1/checklists/templates/:id/upload-signed | Upload signed scan for physical checklist | SURVEYOR | Done | Pending
77 | POST | /api/v1/checklists/templates/:id/assign | Assign template to vessel type/cert type | ADMIN,TM | Done | Pending
78 | DELETE | /api/v1/checklists/templates/:id | Delete checklist template | ADMIN | Done | Pending
🏆 Certificates [/api/v1/certificates]
79 | GET | /api/v1/certificates/verify/:number | Public: verify certificate by number | Public | Done | Done
80 | GET | /api/v1/certificates/types | List all certificate types | All | Done | Pending
81 | POST | /api/v1/certificates/types | Create new certificate type | ADMIN | Done | Pending
82 | GET | /api/v1/certificates/types/:id | Get certificate type by ID | All | Done | Pending
83 | PUT | /api/v1/certificates/types/:id | Update certificate type | ADMIN,TM | Done | Pending
84 | GET | /api/v1/certificates/types/:id/required-documents | Get required docs for cert type | ADMIN,TM | Done | Pending
85 | POST | /api/v1/certificates/types/:id/required-documents | Add required doc to cert type | ADMIN,TM | Done | Pending
86 | PUT | /api/v1/certificates/types/:id/required-documents/:docId | Update required doc rule | ADMIN,TM | Done | Pending
87 | DELETE | /api/v1/certificates/types/:id/required-documents/:docId | Remove required doc rule | ADMIN,TM | Done | Pending
88 | GET | /api/v1/certificates | List all certificates (with filters) | All | Done | Pending
89 | GET | /api/v1/certificates/expiring | List expiring certificates | CLIENT,ADMIN,GM,TM,TO | Done | Pending
90 | GET | /api/v1/certificates/upload-url | Get presigned URL to upload certificate file | ADMIN,GM,TM | Done | Pending
91 | POST | /api/v1/certificates/vessel/:vesselId/external | Upload externally issued certificate | ADMIN,GM,TM | Done | Pending
92 | GET | /api/v1/certificates/vessel/:vesselId | Get all certificates for a vessel | All | Done | Pending
93 | GET | /api/v1/certificates/job/:jobId | Get certificate generated from a job | All | Done | Pending
94 | POST | /api/v1/certificates | Generate certificate draft from job | ADMIN,GM,TM | Done | Pending
95 | PUT | /api/v1/certificates/:id | Update certificate draft fields | ADMIN,GM,TM | Done | Pending
96 | POST | /api/v1/certificates/:id/issue | Officially issue certificate | ADMIN,GM | Done | Pending
97 | GET | /api/v1/certificates/:id | Get certificate full details | All | Done | Pending
98 | GET | /api/v1/certificates/:id/preview | Preview certificate as PDF | All | Done | Pending
99 | GET | /api/v1/certificates/:id/download | Download certificate PDF | All | Done | Pending
100 | POST | /api/v1/certificates/:id/sign | Digitally sign the certificate | ADMIN,GM | Done | Pending
101 | GET | /api/v1/certificates/:id/signature | Get signature info for certificate | All | Done | Pending
102 | PUT | /api/v1/certificates/:id/suspend | Suspend an active certificate | ADMIN,TM | Done | Pending
103 | PUT | /api/v1/certificates/:id/revoke | Revoke certificate permanently | ADMIN,TM | Done | Pending
104 | PUT | /api/v1/certificates/:id/restore | Restore suspended certificate | ADMIN,TM | Done | Pending
105 | PUT | /api/v1/certificates/:id/renew | Renew expiring certificate | ADMIN,TM | Done | Pending
106 | POST | /api/v1/certificates/bulk-renew | Bulk renew multiple certificates | ADMIN,TM | Done | Pending
107 | POST | /api/v1/certificates/:id/reissue | Reissue certificate (new version) | ADMIN,TM | Done | Pending
🏛️ Certificate Authorities [/api/v1/certificates/authorities]
108 | GET | /api/v1/certificates/authorities | List certificate authorities | ADMIN,GM | Done | Pending
109 | POST | /api/v1/certificates/authorities | Add new certificate authority | ADMIN | Done | Pending
110 | GET | /api/v1/certificates/authorities/upload-logo | Get presigned URL for CA logo | ADMIN | Done | Pending
111 | GET | /api/v1/certificates/authorities/:id | Get certificate authority details | ADMIN,GM | Done | Pending
112 | PUT | /api/v1/certificates/authorities/:id | Update certificate authority | ADMIN | Done | Pending
113 | DELETE | /api/v1/certificates/authorities/:id | Delete certificate authority | ADMIN | Done | Pending
📄 Documents [/api/v1/documents]
114 | GET | /api/v1/documents/get-upload-url | Get S3 presigned URL for file upload | CLIENT,ADMIN,GM,TM,SURV | Done | Pending
115 | POST | /api/v1/documents/upload | Upload file directly (multipart) | CLIENT,ADMIN,GM,TM,SURV | Done | Pending
116 | POST | /api/v1/documents/register | Register file after S3 direct upload | CLIENT,ADMIN,GM,TM,SURV | Done | Pending
117 | GET | /api/v1/documents/:id | Get document metadata by ID | All | Done | Pending
118 | GET | /api/v1/documents/:entityType/:entityId | List all docs for an entity (job/vessel) | All | Done | Pending
119 | POST | /api/v1/documents/:entityType/:entityId | Upload document for specific entity | CLIENT,ADMIN,GM,TM,SURV | Done | Pending
120 | POST | /api/v1/documents/:entityType/:entityId/register | Register doc for entity post-S3 upload | CLIENT,ADMIN,GM,TM,SURV | Done | Pending
121 | DELETE | /api/v1/documents/:id | Delete a document | ADMIN,GM | Done | Pending
🔔 Notifications [/api/v1/notifications]
122 | GET | /api/v1/notifications | Get own notifications list | All | Done | Pending
123 | PUT | /api/v1/notifications/:id/read | Mark single notification as read | All | Done | Pending
124 | PUT | /api/v1/notifications/read-all | Mark all notifications as read | All | Done | Pending
✔️ Approvals [/api/v1/approvals]
125 | POST | /api/v1/approvals | Create multi-step approval workflow | ADMIN,GM,TM | Done | Pending
126 | PUT | /api/v1/approvals/:id/step | Approve / reject a specific step | ADMIN,GM,TM | Done | Pending
⚠️ Non-Conformities [/api/v1/non-conformities]
127 | POST | /api/v1/non-conformities | Report a non-conformity finding | SURVEYOR,TO | Done | Pending
128 | PUT | /api/v1/non-conformities/:id/close | Close / resolve NC after correction | TO,TM | Done | Pending
129 | GET | /api/v1/non-conformities/job/:jobId | Get all NCs for a job | ADMIN,GM,TM,TO,SURV | Done | Pending
🚨 Incidents [/api/v1/incidents]
130 | POST | /api/v1/incidents | Report a new incident | CLIENT,ADMIN,GM,TM | Done | Pending
131 | GET | /api/v1/incidents | List all incidents | CLIENT,ADMIN,GM,TM,TO | Done | Pending
132 | GET | /api/v1/incidents/:id | Get incident details | CLIENT,ADMIN,GM,TM,TO | Done | Pending
133 | PUT | /api/v1/incidents/:id/status | Update incident investigation status | ADMIN,GM,TM | Done | Pending
💰 Payments [/api/v1/payments]
134 | GET | /api/v1/payments | List all payments | CLIENT,ADMIN,GM,TM | Done | Pending
135 | GET | /api/v1/payments/summary | Get financial summary / totals | CLIENT,ADMIN,GM | Done | Pending
136 | GET | /api/v1/payments/:id | Get single payment by ID | CLIENT,ADMIN,GM,TM | Done | Pending
137 | POST | /api/v1/payments/invoice | Generate invoice for a job | ADMIN,GM,TM | Done | Pending
138 | PUT | /api/v1/payments/:id/pay | Mark payment as paid (with receipt) | ADMIN,GM,TM | Done | Pending
139 | POST | /api/v1/payments/:id/refund | Process full refund | ADMIN,GM | Done | Pending
140 | POST | /api/v1/payments/:id/partial | Record partial payment | ADMIN,GM,TM | Done | Pending
141 | GET | /api/v1/payments/:id/ledger | View full payment ledger/history | ADMIN,GM | Done | Pending
142 | POST | /api/v1/payments/writeoff | Write off bad debt | ADMIN | Done | Pending
📊 Reports [/api/v1/reports]
143 | GET | /api/v1/reports/certificates | Certificate issuance report | ADMIN,GM,TM | Done | Pending
144 | GET | /api/v1/reports/surveyors | Surveyor performance report | ADMIN,GM,TM | Done | Pending
145 | GET | /api/v1/reports/non-conformities | Non-conformity summary report | ADMIN,GM,TM | Done | Pending
146 | GET | /api/v1/reports/financials | Financial & revenue report | ADMIN,GM | Done | Pending
📌 Activity Requests [/api/v1/activity-requests]
147 | POST | /api/v1/activity-requests | Create activity/service request | CLIENT,ADMIN,GM,TM | Done | Pending
148 | GET | /api/v1/activity-requests | List activity requests | CLIENT,ADMIN,GM,TM,TO | Done | Pending
149 | GET | /api/v1/activity-requests/:id | Get activity request by ID | CLIENT,ADMIN,GM,TM,TO | Done | Pending
150 | PUT | /api/v1/activity-requests/:id/status | Update activity request status | ADMIN,GM,TM | Done | Pending
🔄 Change Requests [/api/v1/change-requests]
151 | POST | /api/v1/change-requests | Submit change request for a job | CLIENT,ADMIN,GM,TM | Done | Pending
152 | GET | /api/v1/change-requests | List all change requests | ADMIN,GM,TM | Done | Pending
153 | PUT | /api/v1/change-requests/:id/approve | Approve a change request | ADMIN,GM | Done | Pending
154 | PUT | /api/v1/change-requests/:id/reject | Reject a change request | ADMIN,GM | Done | Pending
📅 TOCA [/api/v1/toca]
155 | POST | /api/v1/toca | Create TOCA (Technical Certificate) | TM | Done | Pending
156 | PUT | /api/v1/toca/:id/status | Update TOCA status | TM,ADMIN | Done | Pending
157 | GET | /api/v1/toca | List all TOCAs | ADMIN,GM,TM | Done | Pending
🚩 Flags (Port/Flag States) [/api/v1/flags]
158 | POST | /api/v1/flags | Create flag state record | ADMIN | Done | Pending
159 | GET | /api/v1/flags | List all flag states | ADMIN,GM,TM,TO | Done | Pending
160 | GET | /api/v1/flags/:id | Get flag state by ID | ADMIN,GM,TM,TO | Done | Pending
161 | PUT | /api/v1/flags/:id | Update flag state | ADMIN | Done | Pending
⭐ Feedback [/api/v1/feedback]
162 | POST | /api/v1/feedback | Client submits job feedback/rating | CLIENT | Done | Pending
163 | GET | /api/v1/feedback | List all feedback (management view) | ADMIN,GM | Done | Pending
164 | GET | /api/v1/feedback/job/:jobId | Feedback for specific job | ADMIN,GM,CLIENT | Done | Pending
🌟 Portfolio Feedback [/api/v1/portfolio-feedback]
165 | GET | /api/v1/portfolio-feedback/public | Public: get published testimonials | Public | Done | Pending
166 | POST | /api/v1/portfolio-feedback | Submit/update portfolio feedback | CLIENT | Done | Pending
167 | GET | /api/v1/portfolio-feedback/my-feedback | Client: view own portfolio feedback | CLIENT | Done | Pending
168 | GET | /api/v1/portfolio-feedback | Admin: list all portfolio feedback | ADMIN,GM | Done | Pending
169 | PATCH | /api/v1/portfolio-feedback/:id/visibility | Toggle public visibility of feedback | ADMIN | Done | Pending
📞 Contact / Enquiries [/api/v1/contact]
170 | POST | /api/v1/contact | Submit contact/enquiry form (public) | Public | Done | Pending
171 | GET | /api/v1/contact/stats | Enquiry statistics dashboard | ADMIN,GM | Done | Pending
172 | GET | /api/v1/contact | List all enquiries | ADMIN,GM | Done | Pending
173 | GET | /api/v1/contact/:id | Get single enquiry by ID | ADMIN,GM | Done | Pending
174 | PATCH | /api/v1/contact/:id/status | Update enquiry status (read/replied) | ADMIN,GM | Done | Pending
175 | DELETE | /api/v1/contact/:id | Delete enquiry | ADMIN | Done | Pending
🎫 Support Tickets [/api/v1/support]
176 | POST | /api/v1/support | Submit support ticket | All | Done | Pending
177 | GET | /api/v1/support | List all support tickets | All | Done | Pending
178 | GET | /api/v1/support/:id | Get support ticket by ID | All | Done | Pending
179 | PUT | /api/v1/support/:id/status | Update ticket status (open/resolved) | ADMIN,GM | Done | Pending
📜 Compliance (GDPR) [/api/v1/compliance]
180 | GET | /api/v1/compliance/export/:id | Export user data (GDPR data portability) | ADMIN,CLIENT | Done | Pending
181 | POST | /api/v1/compliance/anonymize/:id | Anonymize user data (GDPR right to forget) | ADMIN | Done | Pending
🔎 Global Search [/api/v1/search]
182 | GET | /api/v1/search | Global search across vessels, jobs, clients | All | Done | Pending
📈 Dashboard [/api/v1/dashboard]
183 | GET | /api/v1/dashboard | Role-specific dashboard stats & metrics | All | Done | In Progress
📧 Email Templates [/api/v1/templates]
184 | POST | /api/v1/templates | Create email/doc template | ADMIN | Done | Pending
185 | GET | /api/v1/templates | List all templates | ADMIN,GM,TM | Done | Pending
186 | GET | /api/v1/templates/:id | Get template by ID | ADMIN,GM,TM | Done | Pending
187 | PUT | /api/v1/templates/:id | Update template content | ADMIN | Done | Pending
188 | DELETE | /api/v1/templates/:id | Delete template | ADMIN | Done | Pending
🌐 Site Static Content [/api/v1/site-static]
189 | GET | /api/v1/site-static | List published pages (public) | Public | Done | Pending
190 | GET | /api/v1/site-static/:slug | Get page by slug (public) | Public | Done | Pending
191 | POST | /api/v1/site-static | Create new static page | ADMIN | Done | Pending
192 | PUT | /api/v1/site-static/:slug | Update page by slug | ADMIN | Done | Pending
193 | DELETE | /api/v1/site-static/:slug | Delete page by slug | ADMIN | Done | Pending
194 | GET | /api/v1/site-static/admin/:id | Admin: get page by ID (incl. drafts) | ADMIN | Done | Pending
195 | PUT | /api/v1/site-static/admin/:id | Admin: update page by ID | ADMIN | Done | Pending
196 | DELETE | /api/v1/site-static/admin/:id | Admin: delete page by ID | ADMIN | Done | Pending
📰 Newsletter [/api/v1/newsletter]
197 | POST | /api/v1/newsletter/subscribe | Subscribe to newsletter | Public | Done | Pending
198 | POST | /api/v1/newsletter/unsubscribe | Unsubscribe from newsletter | Public | Done | Pending
199 | GET | /api/v1/newsletter/unsubscribe-one-click | One-click unsubscribe (from email) | Public | Done | Pending
200 | GET | /api/v1/newsletter/subscribers | List all subscribers | ADMIN | Done | Pending
201 | POST | /api/v1/newsletter/send | Broadcast email to all subscribers | ADMIN | Done | Pending
🎥 Website / Videos [/api/v1/website]
202 | GET | /api/v1/website/videos | List website video gallery (public) | Public | Done | Pending
203 | POST | /api/v1/website/videos | Upload new video with thumbnail | ADMIN | Done | Pending
204 | PUT | /api/v1/website/videos/:id | Update video metadata | ADMIN | Done | Pending
205 | DELETE | /api/v1/website/videos/:id | Delete video | ADMIN | Done | Pending
🌍 Public Endpoints [/api/v1/public]
206 | GET | /api/v1/public/certificate/verify/:number | Verify certificate (public portal) | Public | Done | Done
207 | GET | /api/v1/public/vessel/:imo | Verify vessel by IMO number | Public | Done | Pending
208 | GET | /api/v1/public/website/videos | Get website video gallery | Public | Done | Pending
⚙️ System / Admin Ops [/api/v1/system]
209 | GET | /api/v1/system/health | Server health check | Public | Done | N/A
210 | GET | /api/v1/system/readiness | DB/cache readiness check | Public | Done | N/A
211 | GET | /api/v1/system/version | API version info | Public | Done | N/A
212 | GET | /api/v1/system/metrics | Server performance metrics | ADMIN | Done | N/A
213 | GET | /api/v1/system/audit-logs | Full system audit logs | ADMIN | Done | Pending
214 | POST | /api/v1/system/users/:id/logout | Force logout a user | ADMIN | Done | Pending
215 | GET | /api/v1/system/migrations | View DB migration status | ADMIN | Done | N/A
216 | GET | /api/v1/system/jobs/failed | View failed background jobs | ADMIN | Done | N/A
217 | POST | /api/v1/system/jobs/:id/retry | Retry failed background job | ADMIN | Done | N/A
218 | POST | /api/v1/system/maintenance/:action | Trigger maintenance action | ADMIN | Done | N/A
219 | GET | /api/v1/system/feature-flags | View feature flags | ADMIN | Done | N/A
220 | GET | /api/v1/system/locales | View supported locales | ADMIN | Done | N/A

## 📊 Summary
📊 GR-Class — API Module-wise Progress Summary
Module | Total APIs | ✅ BE Done | ⏳ BE Pending | ✅ FE Done | ⏳ FE Pending
🔐 Authentication | 6 | 6 | 0 | 4 | 2
👤 Users | 8 | 8 | 0 | 1 | 7
🏢 Clients | 10 | 10 | 0 | 0 | 10
🚢 Vessels | 5 | 5 | 0 | 0 | 5
🔍 Surveyors | 12 | 12 | 0 | 0 | 12
💼 Jobs | 20 | 20 | 0 | 0 | 20
📋 Surveys | 7 | 7 | 0 | 0 | 7
✅ Checklists | 2 | 2 | 0 | 0 | 2
📝 Checklist Templates | 8 | 8 | 0 | 0 | 8
🏆 Certificates | 29 | 29 | 0 | 1 | 28
🏛️ Certificate Authorities | 6 | 6 | 0 | 0 | 6
📄 Documents | 8 | 8 | 0 | 0 | 8
🔔 Notifications | 3 | 3 | 0 | 0 | 3
✔️ Approvals | 2 | 2 | 0 | 0 | 2
⚠️ Non-Conformities | 3 | 3 | 0 | 0 | 3
🚨 Incidents | 4 | 4 | 0 | 0 | 4
💰 Payments | 9 | 9 | 0 | 0 | 9
📊 Reports | 4 | 4 | 0 | 0 | 4
📌 Activity Requests | 4 | 4 | 0 | 0 | 4
🔄 Change Requests | 4 | 4 | 0 | 0 | 4
📅 TOCA | 3 | 3 | 0 | 0 | 3
🚩 Flags (Port/Flag States) | 4 | 4 | 0 | 0 | 4
⭐ Feedback | 3 | 3 | 0 | 0 | 3
🌟 Portfolio Feedback | 5 | 5 | 0 | 0 | 5
📞 Contact / Enquiries | 6 | 6 | 0 | 0 | 6
🎫 Support Tickets | 4 | 4 | 0 | 0 | 4
📜 Compliance (GDPR) | 2 | 2 | 0 | 0 | 2
🔎 Global Search | 1 | 1 | 0 | 0 | 1
📈 Dashboard | 1 | 1 | 0 | 0 | 1
📧 Email Templates | 5 | 5 | 0 | 0 | 5
🌐 Site Static Content | 8 | 8 | 0 | 0 | 8
📰 Newsletter | 5 | 5 | 0 | 0 | 5
🎥 Website / Videos | 4 | 4 | 0 | 0 | 4
🌍 Public Endpoints | 3 | 3 | 0 | 1 | 2
⚙️ System / Admin Ops | 12 | 12 | 0 | 0 | 12
TOTAL (35 modules) | 220 | 220 | 0 | 7 | 213
— STATUS LEGEND —
✅ Done | 🔄 In Progress | ⏳ Pending | — N/A